## FY19
Strategic Goal | Objective | Action Item | FY18 Champion | FY18 SMART Goal | Quarterly Update Highlights (5/18) | FY18 Status | FY19 Decision | FY19 Champion | FY19 SMART Goal | August 2018 Update | August 2018 Status | September 2018 Update | September 2018 Status | October 2018 Update | October 2018 Status | November 2018 Update | November 2018 Status | December 2018 Update | December 2018 Status | January 2019 Update | January 2019 Status | February 2019 Update | February 2019 Status | March 2019 Update | March 2019 Status | April 2019 Update | April 2019 Status | May 2019 Update | May 2019 Status | June 2019 Update | June 2019 Status
Strategic Goal 1: Benchmarks, best practices, and metrics | Objective A: Strengthen the position of libraries within their institutions by identifying benchmarks, best practices, and metrics which align with accrediting standards (HLC, ICCB, etc.). | 1.A.1: Create assessment and metrics repository | Cate Kaufman and Karen Becker (Board Liaison), Benchmarks Working Group Co-Chairs | Using IPEDS and ACRL reports begin collecting some baseline data | Collected data from 15 NILRC institutions. | Action complete | continuing | Cate Kaufman and Karen Becker (Board Liaison), Benchmarks Working Group Co-Chairs | Increase participation in data collection by 10%. Develop a guide for survey participants before next collection cycle. | Second round of collection solicition took the total number of respondents from 16 to 25 | 10% increase in data collection has been reached in this first cycle | A session focusing on how to use data collected has been planned for the Allerton retreat. Beginning to discuss long term process for data collection and analysis | Progressing
Strategic Goal 1: Benchmarks, best practices, and metrics | Objective A: Strengthen the position of libraries within their institutions by identifying benchmarks, best practices, and metrics which align with accrediting standards (HLC, ICCB, etc.). | 1.A.2: Share data and best practices amongst member institutions | Cate Kaufman and Karen Becker (Board Liaison), Benchmarks Working Group Co-Chairs | Develop a tool by which data is stored, maintained and shared to the membership | The committee will analyze data and share findings at May 10 Council of Delegates Meeting and send results through the listserv/member portal. | Action complete | continuing | Cate Kaufman and Karen Becker (Board Liaison), Benchmarks Working Group Co-Chairs |  |  |  | Continue discussing various options but no recommendations at this time | Progressing
Strategic Goal 1: Benchmarks, best practices, and metrics | Objective A: Strengthen the position of libraries within their institutions by identifying benchmarks, best practices, and metrics which align with accrediting standards (HLC, ICCB, etc.). | 1.A.3: Develop recommendations for minimum standards for library operations | Cate Kaufman and Karen Becker (Board Liaison), Benchmarks Working Group Co-Chairs | (TBD) |  | Action on hold | hold | This Action Item will not be addressed this fiscal year | none | no action | no action | no action | no action | no action | no action | no action | no action
Strategic Goal 2: Professional development | Objective A: Provide a wide-range of professional development opportunities in a variety of modalities. | 2.A.1: Maintain two in-person conferences each year | Aimee Walker, Allerton Chair (Lisa Sikora, Board Liaison) and Emily Vescogni, Learning Innovations Conference Chair (Ashtin Trimble, Board Liaison) | A. Appoint new committee leadership prior to the end of the current Board year. B. Document planning procedures, policies, promotion, and timelines for future planning committees by the end of the Board year. C. Develop guidelines and criteria for awarding Allerton sponsorships to be approved by the Board and communicated to the membership prior to sending out the call for presenters in March 2018. | Three lightning talks scheduled for May Council of Delegates meeting due to cancellation of LIC. Waiting for ILCCO June meeting--more information available after that on the future of LIC. | Allerton: -Action progressing LIC: -Action progressing with challenges | continuing | Stephanie King, Allerton Chair (Lisa Sikora, Board Liaison) and Ashtin Trimble, Learning Innovations Conference Board Liaison | LIC: Hold one annual conference in partnership with ILCCO. | LIC: planning meeting 8/6, survey distributed, 8/20 follow-up meeting scheduled, committee recruitment continues | LIC: progressing | LIC: met 8/20; conference scheduled for Friday, April 26 at Richland CC; Call for Proposals has been distributed; Proposals due Oct 1. | LIC: Progressing Allerton: Registration closes 9/13. Five first time attendees. 21 registered. | LIC: Call for proposals extended | LIC: progressing | LIC: Call for proposals still open. Looking for more ILCCO presentations. Preparing agend and save the date. | LIC: progressing | LIC: Met on 11/19. Proposals accepted. Finalizing agenda and room assignments. Meeting scheduled 1/28. Registration opens in Feb. | LIC: progressing. Allerton met Dec. 12. Call for proposals will be sent out in January. Theme of the conference is being finalized.
Strategic Goal 2: Professional development | Objective A: Provide a wide-range of professional development opportunities in a variety of modalities. | 2.A.2: Conduct two online/multimedia learning opportunities each year | Bryan Clark, Information Literacy Chair (Beth Mandrell, Board Liaison) | Plan, schedule, and run webinars on a variety of informative topics by professionals in our field using online meeting spaces at least twice during the fiscal year. | The committee ran three webinars this year, exceeding their target of two. | Action complete | continuing | Bryan Clark, Information Literacy Chair (Spencer Brayton, Board Liaison) | Plan, schedule, and run webinars on a variety of informative topics by professionals in our field using online meeting spaces at least twice during the fiscal year. | Committee will be meeting later this month. | progressing | Committee pooled ideas for webinars from Facebook as well as from our August meeting. | progressing | Committee picked a topic and a team of presenters to come up with a date. The first webinar will be Thursday, November 29th at 10am on "finding freely reusable and/or modifiable multimedia content online". | progessing | The committee is working on creating content for our upcoming webinar. We are also starting to think about dates for the spring semester. | progressing | The Info Lit Committee held its first webinar of the fiscal year on November 29th. The recording is availabe on the listserv and on the NILRC website. It went well, and there was positive feedback overall. | progressing | We have set the topics for our next two webinars. 'Data Analytics' will be held at the end of Feb/beginning of March. 'Collaboration with High Schools' will be held at the end of April. No specific dates have been set. | progressing
Strategic Goal 2: Professional development | Objective A: Provide a wide-range of professional development opportunities in a variety of modalities. | 2.A.3: Provide professional development activities on emerging and member-requested topics | This Action Item will not be addressed this fiscal year |  |  | No action | NEW | Terra Jacobson and Spencer Brayton, Outreach Team Co-Chairs/Hilary Meyer, Chair; Micheal Kott PDC Chair | none | - Investigating opportunities with ICCCA - Investigating opporunities to work with other IL organizations adjacent to libraries | progressing | Talked with RAILS about unserved patrons in IL. -terra | progressing |  |  | -As a result of Allerton and Town Hall feedback on member needs, Board reinstating Professional Development Committee to tackle member-requested topics in an accessible format (asynchronous) | progressing | Micheal Kott has agreed to serve as Chair of PDC, we've gotten a few volunteers and will put out a call for more in January. Micheal attended the December Board Meeting. | progressing
Strategic Goal 3: Networking and collaboration | Objective A: Provide opportunities for networking and collaboration. | 3.A.1: Explore deeper partnerships with other organizations such as ICCCA and ILCCO | Beth Mandrell (Board Liaison), NILRC Past Chair, Liaison to ICCCA and ILCCO | A: Participate in ICCCA meetings/conferences/workshops in order to strengthen the relationship between NILRC and ICCCA. B: Plan and coordinate with ILCCO to offer the annual Learning Innovations Conference. | Continuance of communication with both organizations through meeting attendance. | Action progressing | continuing | Terra Jacobson (Board Liaison), NILRC Past Chair, Liaison to ICCCA and ILCCO | A. Connect with ICCCA membership to determine increased participation of NILRC in the FY20 conference. B. Deveop program for FY20 conference proposal about the value of libraries for community colleges. | Waiting to heard fomr ICCCA | no action | Talked with ICCCA about this years conference, need to push our presentation and proposal to 2020. | progressing with challenges
Strategic Goal 3: Networking and collaboration | Objective A: Provide opportunities for networking and collaboration. | 3.A.2: Establish a plan for long-term listserv maintenance and development to potentially include lists for specific job categories at member institutions | This Action Item will not be addressed this fiscal year |  |  | No action | NEW | Hilary Meyer | Work on staff engagement will inform this Action Item | Specific action on hold as we gather input | on hold | Specific action on hold as we gather input | on hold |  |  | -Allerton/Town Hall feedback led to reinstatement of Professional Development Committee which will include moderating focused listservs | progressing | PDC getting going this Spring. | progressing
Strategic Goal 3: Networking and collaboration | Objective A: Provide opportunities for networking and collaboration. | 3.A.3: Investigate partnerships in contiguous states to identify additional institutions who may benefit from participation in NILRC | Lisa Sikora (Board Liaison), Executive Office Business Manager | Present potential membership list to the Board by the end of the year. | No progress due to time constraints | Action on hold | hold | This Action Item will not be addressed this fiscal year | none | no action | no action | no action | no action | no action | no action | no action | no action | no action | no action
Strategic Goal 3: Networking and collaboration | Objective B: Engage staff at member institutions. | 3.B.1: Share information through in-person opportunities such as through regional meetings which could engage staff at all levels of member institutions | This Action Item will not be addressed this fiscal year |  |  | No action | NEW | Terra Jacobson and Spencer Brayton, Outreach Team Co-Chairs | Reach out to non-member institutions via email to understand their needs and why they aren't members. | - See 2.A.3 update - Reach out to non-members (invite via sponsorship to Allerton?) | Emails sent, awaiting responses. | [6 empty] | This action will also be accomplished through reinstated PDC | progressing
Strategic Goal 3: Networking and collaboration | Objective B: Engage staff at member institutions. | 3.B.2: Communicate opportunities for networking and collaboration through multiple channels to increase staff awareness of NILRC events | Terra Jacobson (Board Liaison), NILRC Board Chair, and Board Members Amy Jo Caulkins | A. Develop a quarterly newsletter that will be distributed in August, November, February, & May (during the school year to reach the most library employees). To be published by Terra and content created by the board. B. Create a NILRC social media presence to share information between institutions as reach non-delegate members. Post on social media account 1 time per week. Relay information from board meetings to members. | A: The Board agreed the newsletter cost-benefit was not as worthwhile as focusing on more interactive, engaging, and timely social media (FB) efforts. B. Created Facebook account with help from Amy Jo. Guidelines have been created and distributed, with a call out to members to join. | A: Action on hold B: Action progressing with challenges | continuing | Hilary Meyer, NILRC Chair, Amy Jo Caulkins (social media), Terra Jacobson and Spencer Brayton, Outreach Team Co-Chairs | Send letters to membership at least quarterly via listserv (HM) | Planning first letter for 8/17 | Action progressing | Been posting regularly to FB page, need to increase membership and plan for posts. - TJ | progressing | Amy Jo has left |  | -November Town Hall (promoted through FB, listserv, website) resulted in additional member interest, including signing up for the listserv | progressing | Also through reinstated PDC | progressing
Strategic Goal 3: Networking and collaboration | Objective B: Engage staff at member institutions. | 3.B.3: Develop a new staff program to inform them of NILRC’s offerings and provide a platform for connections to colleagues at member institutions | This Action Item will not be addressed this fiscal year |  |  | No action | NEW (Planning) | Terra Jacobson and Spencer Brayton, Outreach Team Co-Chairs | Investigate new opportunities, for example reaching out to new directors with a packet of information about NILRC. | - See 3.B.1 - more to be done in this area | progressing | [6 empty] | Also through reinstated PDC | progressing
Strategic Goal 3: Networking and collaboration | Objective B: Engage staff at member institutions. | 3.B.4: Craft a plan to continually maintain and develop the overall usefulness of the NILRC website for members | Amanda Wiesenhofer, Website Chair (Amy Jo Caulkins, Board Liaison) | A. Develop a survey to send out to NILRC membership regarding the usefulness of the NILRC website. B. Seek out suggestions for improvement from membership; suggestion form on website? C. Communicate changes and improvements made to the website at NILRC functions (like presenting at Allerton); offer membership the opportunity to ask questions and offer suggestions. | A. The committee collected and discussed results from the survey sent out to NILRC members. We will be adding a site map to the NILRC website soon. B. The committee gathered and reacted to suggestions provided at the Allerton Conference, and have added a website suggestion form to the bottom of the Members Portal page. C. We presented at Allerton, have implemented navigational improvements, and have created a suggestion form. D. Amy Jo created a Facebook Group for NILRC members. The committee compiled a draft list of “Dos and Don’ts” that will serve as a guideline. | A. Action progressing B. Action complete C. Action complete D. Action complete | continuing | Amanda Wiesenhofer, Website Chair and Board Liaison | Create "Help" page on website. Purpose will be to help users navigate site/locate information, but can also include resources to assist with using Google Drive for creating and sharing documents. | Rough outline of Help page is drafted. Need to discuss what type of tutorial/information is needed for Google Drive. | Action progressing | Draft Help page has been created. Will show updates/improvements to the site at Allerton and answer questions/seek feedback. Added a help with Google Drive page, which includes a contact form to request one-on-one virtual training/assistance. | Action Progressing | Presented draft help page and website modifications at Allerton, and received excellent feedback. Committee met on October 1st and discussed suggestions feedback in order to begin modifications on the following: changes to main navigational structure, reorganizing/relabeling Member Portal page, modifying storage and access of NILRC materials from meetings and presentations. Main navigational changes are done. Everything else in progress. Still need to discuss adding image labels and library links to images. | Action progressing | Decision: move the full Strategic Plan document from the portal, and place it on the public-facing side of the site. Proposed changing the links on the Membership page from links to member institutions to links to member institution libraries (or other webpages at the institutions' discretion) instead. Will contact member libraries regarding this change in the near future. Changed hyperlink color from blue to red to increase visibility; created page called "Presentation Materials," which is accessible from Member Portal to provide access to presentation materials and videos organized by Committee/Conference/Event. | Progressing | Strategic Plan moved. Modifying PowerPoint on Google Drive & NILRC to include information about default share settings and changing share settings at the subfolder and document level. This form will be used for ongoing training and orientation for new Committee and Board members. Creating form to send to NILRC Delegates; will ask what URL (institution, Library, LRC, Distance Ed) they would like to share with the public on the NILRC "Membership" webpage. | Progressing | Met via email the week of 1.07.19. Modified the Google Drive & NILRC PowerPoint Document to include information on default share settings for folders & documents and changing share settings for folders & documents. Created draft survey for collecting Library/Institutional URLs from member libraries. Will revise survey and prepare to distribute to membership. | Progressing
Strategic Goal 3: Networking and collaboration | Objective B: Engage staff at member institutions. | 3.B.5: Support staff attendance at events through scholarship opportunities | This Action Item will not be addressed this fiscal year |  |  | No action | continuing | Hilary Meyer, NILRC Chair, and Scott Drone-Silvers, Treasurer | Communicate available scholarships to staff via listserv/social media/town halls
Strategic Goal 4: Innovation | Objective A: Seek out innovative initiatives to advance services. | 4.A.1: Lead the development of the library’s role in Open Educational Resources (OER) within Illinois community colleges | This Action Item will not be addressed this fiscal year |  |  | No action | NEW (Ashtin environmental scan) | Ashtin Trimble | Investigate OER initatives at CARLI and ILCCO. | Emails sent to CARLI and ILCCO representatives. Still awaiting one response. | progressing | No update | progressing | No update | progressing | OER discussion for Illinois stakeholders on Nov. 26. Organized and led by Jeff Newell, ICCB. Hilary, Ashtin, Frances plan to attend. COD OER Summit Nov. 30. | progressing | OER IL stakeholders meetings, organized by ICCB, held 11/26 and 12/12. 31 IL CCs attended the OER Summit on 11/30 | progressing
Strategic Goal 4: Innovation | Objective A: Seek out innovative initiatives to advance services. | 4.A.2: Investigate and communicate information regarding cutting edge technologies | This Action Item will not be addressed this fiscal year |  |  | No action | hold | This Action Item will not be addressed this fiscal year | none | no action | no action | no action | no action | no action | no action | no action | no action | no action | no action
Strategic Goal 4: Innovation | Objective A: Seek out innovative initiatives to advance services. | 4.A.3: Provide group buy opportunities for emerging technologies | Lisa Sikora (Board Liaison), Executive Office Business Manager, and TBD Member Volunteer | Continue to appraise membership of new opportunities to purchase goods and services through use of the listserv. | Negotiated a contract with Brainfuse. In talks with RedLink for Library Dashboard. Talking with Swank. Talking with Smarthinking about how to increase sales. | Action progressing | hold | This Action Item will not be addressed this fiscal year | none | no action | no action | no action | no action | no action | no action | no action | no action | no action | no action
Strategic Goal 4: Innovation | Objective A: Seek out innovative initiatives to advance services. | 4.A.4: Encourage member-driven ideas through feedback opportunities such as surveys, open online forums, informal networking opportunities at existing conferences, and a dedicated rotating Board agenda item for member institutions | Terra Jacobson (Board Liaison), NILRC Board Chair, and Lisa Sikora, Executive Office Business Manager | A. Create a portion of the NILRC Network newsletter to ask for feedback on services or conduct surveys (this is a quarterly newsletter). B. Establish a social media presence to informally gather feedback from member institutions and share opinion surveys. (1 per month). C. Establish a NILRC meetup or sponsorship event at CC conferences in the state (2 per year). D. Require sessions for committees at the annual Allerton Conference to allow time for feedback or programming related to strategic goals, committees and working groups. | A. Focusing on social media (FB) instead of the newsletter. B. Created social media presence, but have not yet developed surveys C. Have considered but many opportunities for this year have been cancelled (learning innovations) D. Will require at next Allerton Conference. | A. Action progressing B. Action progressing C. Action progress stalled D. Action progressing | continuing | Terra Jacobson and Spencer Brayton, Outreach Team Co-Chairs, Amy Jo Caulkins (social media), Hilary Meyer, Chair | A. Create questionaire for non-NILRC community colleges to solict feedback about membership and email to non-members. | - Looking into opportunties at other conferences and with other groups adjacent to libraries. - More to be done in this area. | progressing | Waiting for feedback, has been slow will contact again | progresssing |  |  | -Held Virtual Town Hall Nov. 8, reached additional members | progressing | Also through reinstated PDC | progressing
Strategic Goal 4: Innovation | Objective A: Seek out innovative initiatives to advance services. | 4.A.5: Expand innovation beyond technology to leverage our combined resources effectively | This Action Item will not be addressed this fiscal year |  |  | No action | hold | This Action Item will not be addressed this fiscal year | none | no action | no action | no action | no action | no action | no action | no action | no action | no action | no action
Operational Goal | Objective | Action Item | FY18 Champion | FY18 SMART Goal | Quarterly Update Highlights (5/18) | FY18 Status | FY19 Decision | FY19 Champion | FY19 SMART Goal | August 2018 Update | August 2018 Status | September 2018 Update | September 2018 Status | October 2018 Update | October 2018 Status | November 2018 Update | November 2018 Status | December 2018 Update | December 2018 Status | January 2019 Update | January 2019 Status | February 2019 Update | February 2019 Status | March 2019 Update | March 2019 Status | April 2019 Update | April 2019 Status | May 2019 Update | May 2019 Status | June 2019 Update | June 2019 Status
Operational Goal 1: Future planning | Objective A: Document Policies & Procedures, including succession planning | O1.A.1: Define, prioritize, and update/create necessary policies and procedures, including succession planning | Scott Drone-Silvers and Hilary Meyer | Update employee manual | project on hold | Action on hold | continuing | Frances Whaley, NILRC Chair Elect | A. Create updated policy handbook format. B. Create or update policies, with feedback from the Board. | Policy models used to draft travel policy. Team will incorporate Board feedback into edits. Next policy: credit card usage | progressing
Operational Goal 1: Future planning | Objective B: Ensure ongoing fiscal health of the organization | O1.B.1: Explore additional revenue opportunities as well as increasing organizational capacity | Terra Jacobson | Increase member dues | Board agreed to a $50 increase in each of 2 years | Action complete | continuing | Hilary Meyer, Chair and Scott Drone-Silvers, Treasurer | Investigate options and recommend at least 1 new way to increase revenue and 1 new way to reduce costs (include $ amounts) | Reviewing eresource spend, discussing alternative memberships | Action progressing | Continue exploring alternative membership offerings | Action progressing